## AmberS questions
Item | Questions | Owner | RK comment | PEGA comment 0303 | Concall 0309 | PEGA comment 0317 | Sanshin_0323 | Pegatron 0511
1 | The BT stack developed by RK include any open source , or it is pure in-house development by RK ? | System PM | BT stack是基于LwBT代码，RK在上面做了很多的修改和完善 | [Pega-160303] If we change BT chip from Realtek RTL8761 to CSR8811, CSR8811 BT stack also runs on host side, not on BT chip. Will RK also use BT stack based on lwBT to modify for use with CSR8811? | RK use the same BT stack for CSR8811 | Could RK issue the official letter to declare no use of open source [0318] Sanshin will confirm no use of open source code by email by 3/25 and official declaration will be provided upon request | Please wait for a moment while we are discussing the open source issue with Sony. Sony will make the judgment, not us. Once any feedback from Sony will let you know soon. | With CSR8811, BT stack must runs on host side, i.e. RK NANO-D. Please RK confirm - BT stack open source issue discussion conclusion between Sanshin and Sony - BT stack on NANO-D ownership (the condition is BT chip CSR8811) - When can RK release BT stack with A2DP source and AVRCP target profile support? - How can RK validate released BT stack running on NANO-D works fine with CSR8811 before release to Pegatron? "Works fine" means BT pair/connect/A2DP source/AVRCP control function behaves correctly and normally
2 | Please provide detailed spec of BT, including - BT core spec version (3.0? 4.0? 4.1? 4.2?) - BLE support or not - Supported profile list, including role (A2DP source or sink or both? AVRCP target or controller or both) and version (AVRCP 1.3? 1.4? or 1.5?)  To communicate with BT headset, the minimum required profile is A2DP source and AVRCP target |  | bt core spec version is 4.0 support ble spp. Profile list : A2DP Sink/soure 1.3 AVRCP Sink/sourec 1.3 SPP 1.2 HFP 1.6 | [Pega-160303] 1. HFP is handsfree role or audio gateway role? or both? 2. Can we use conf or xml file to turn on/off one profile or role supported or not? For example, if we don't want to support HFP or A2DP sink (just want A2DP source), can we turn off HFP support by modifying conf or xml file? | RK will disable unnecessary BT profile
3 | The demo board and test tool for BT function. Pega want to evaluate BT function asap | System PM | Demo Board的申请需要走业务流程，请联系业务申请，技术人员没有办法提供； |  | RK sales can provide EVB for Pega PM | Pega need NanoD EVB to evaluate BT performance ASAP, in particular, we worry SBC and SRC need 70MHz [0318] RK Stanley will help confirm with HQ again when EVB can be provided and reply by 3/21
4 | Please provide the test files of new CODEC (FLAC, Linear PCM, Apple Lossless) | System PM | 支持Flac、ALAC等格式的音频解码，需要在项目确定之后再进行移植，目前无法提供； | [Pega-160306] 請確認目前到底有沒有support or Demo可以進行實驗。 | RK need 1w to port to Olive codebase and more time for stability. RK can provide SDK and test file for Pega PM | Pega need NanoD SDK and audio codec test files (FLAC, Linear PCM, Apple Lossless) [0318] RK Stanley will help confirm FLAC SDK ready schedule by 3/21 |  | Need SDK and audio codec test files to verify on RK EVB
5 | The supported format of voice recording file (WAV only ?) | Sanshin | 目前录音仅支持wav | [Pega-160308] Need MP3 format | Pega PM will check mp3 encode license | Narita will handle mp3 license. Can RK support mp3 recording ? [0318] Need RK to study if they can support mp3 encoding by SW | The SDK can not support mp3 recording
6 | Does the BT stack have BT SIG QDID record? If yes, please provide QDID number |  | 目前NanoC有客户已经做过BQB认证，RK自己没有做过相关认证； | [Pega-160303] 1. What is the host side OS? 2. Does NanoC customer BQB also have A2DP source and AVRCP target support? Is the used BT chip RTL8761? | RK customer use NanoC (RK RTOS) to pass BQB which incl. source/sink. SBC encoding is performed by host SoC and UART baudrate is 1.5Mbps
7 | Is the BT stack RK released binary only or source code? |  | binary only
8 | Please BT stack able to record hci dump or snoop log | Sanshin | host debug log | [Pega-160303] 1. Does host debug log you mentioned contain HCI raw data printout? 2. Can we modify the debug level dynamically? | RK can't record HCI raw data due to RAM limitation Pega will ask CSR for other solution. RK must provide a way to enable/disable or change host debug log level dynamically | [Pega-160316] 1. CSR does not have tool to log HCI data but have SPI debug interface with PC to config/debug CSR chip, not involving RK host SoC 2. Per 3/3 con-call, please RK provide a way to enable/disable or change host debug level dynamically for RK and QTC to save log | RK will not support record hci dump or snoop log and only support UART debug. | Still not support record hci dump using CSR 8811?
9 | Please provide BT test tool to enter BT test mode for RF test |  | BT IC Vendor may provide RF test tool | [Pega-160303] 1. Because Nano-D OS is not common OS, the RF test tool RF IC vendor provided may be unable to run on Nano-D OS and based on RK-modified host BT stack. If this case, will RK make sure BT IC vendor RF tool able to run on Nano-D OS and RK BT stack? | RK can help to port CSR test tool on NanoD
10 | In addition to BT stack released, please also release SDK/API document or webpage link |  | OK |  | RK can release BT stack API
13 | NanoD CPU usge while BT stack is doing data transfer. |  | for sbc encode and ssrc need 70Mhz | [Pega-160306] 1. 這樣會不會影響到playlist顯示與造成performance問題 2. 如果改用CSR 8811 SBC encode在BT chip上會需要多少CPU computation power? | Need to check with CSR where SRC is done. If SBC encode is done by CSR chip but SRC is done by RK side, RK thnks SRC only needs 30Mhz. | [Pega-160316] CSR replied that on-chip SBC encoding is disabled by default, so SBC encoding including SRC is done by RK host OS.
14 | BT stack ready leadtime - If we change BT chip from Realtek RTL8761 to CSR8811, how about RK's lead time for BT host stack ready with CSR8811? - What kinds of sanity test will RK perform to make sure BT host stack is ready enough to provide Pegatron? |  |  |  | RK will do sanity BT test and provide test result and change list for Pega when SDK is released
15 | UART protocol support CSR8811 suggests UART communication protocol uses UART_BCSP instead of UART_H4. - Can Nano-D OS UART driver can support UART_BCSP or UART_H4 (UART_BCSP support is better)? - If UART_BCSP is not supported, at least UART_H4 must be supported. However, based on CSR agent saying, if using UART_H4, it may need additional modification or adjustment for communication with CSR8811 (CSR agent says there is no application note provided by CSR, it must be trial-and-error) | Sanshin |  |  | Pega will check BCSP is same as H5 or not | [Pega-160316] 1. BSCP and H5 are different protocol. On Linux, they are also different kernel configurations - H4: CONFIG_BT_HCIUART_H4 - BCSP: CONFIG_BT_HCIUART_BCSP - H5: CONFIG_BT_HCIUART_3WIRE 2. CSR strongly suggests to use RK host OS to use BCSP as UART protocol to communicate because BCSP is easy to communicate between host OS and CSR8811, but H4 it will need taking many effort to let H4 work with CSR8811 |  | With CSR8811, CSR strongly suggests host UART protocol uses UART_BCSP instead UART_H4. Please RK confirm - Will RK implement UART_BCSP? - If yes, SW with UART_BCSP support release date? Should be the same or before BT host stack release date - If no, what is RK's plan when meeting UART communication problem or BT bringup problem with CSR8811?
16 | BT UART baudrate Check with CSR agent, they mentions the suggested BT UART baudrate is 3Mbps to make sure A2DP streaming smooth. What is the maximum UART baudrate RK Nano-D can support? |  |  |  | RK will confirm if 1.5M and 4M baudrate is ok | [Pega-160316] CSR still hopes (not MUST) host UART baudrate can over 3Mbps because they can ensure UART baud rate will effect throughput performance
17 | SBC encode problem If we choose to use CSR8811 as BT chip, CSR8811 chip supports SBC encoding on chip. For this case, can RK SW support SBC encoding location change from host (Nano-D) to BT chip (CSR8811)? |  |  |  | Pega will check SSRC is done by RK or CSR? and the maximum sample rate if SSRC is done by CSR? | [Pega-160316] CSR replied that on-chip SBC encoding is disabled by default, so SBC encoding including SRC is done by RK host OS. This item can be closed

## Olive postmortem
# | Item | 補足 | Owner | PEGA Comment | Concall 0317 | Sanshin_0323
1 | 依照讀音假名分類 | Sony預計提供Librarian and might release image for Olive | System PM | [3/4] Check with RK on Unicode order | Narita將提供library給RK porting | Please wait for a moment while we are discussing the open source issue with Sony.
2 | 追加Index search 假名Tag |  | SW | [3/4] Check with RK on Unicode order | Pega will own this task based on task 1 above | Please wait for a moment while we are discussing the open source issue with Sony.
3 | 修正起動/結束/操行系操作時的POP音・POP NOISE | Please check "POP NOISE" sheet | SW | [3/4] need to discuss with EE internally | Pega will pay attention to new project design and avoid this issue | Please wait for a moment while we are discussing the open source issue with Sony.
4 | 改善展示PLAY LIST內音樂的速度 | 選擇play list到顯示全部的音樂花時間這一點需要改善 | Sanshin | [3/4] Check with RK | Olive : 500首 16s NW-S14 (MSC mode) : 500首 < 1s E580: 500首 < 8s RK是否能改善開啟playlist所需的時間? | Please wait for a moment while we are discussing the open source issue with Sony.
5 | Database的更新時間縮段 | Need data structure improvement. In reference, No matter how many songs in device, adding one song only take less than 10 seconds. It looks like RK need to re-create the database instead of adding into the database. | Sanshin | [3/4] Check with RK | 假如device裡面本來就有放1000首歌話, 這時候再放一首歌進去 , 這時候NW-S14(MSC only)只會Media update這一首歌而已(小於10sec) , 而Olive 卻要Media update 1001首, 這時候就會很慢(約15sec), RK是否能改善Media update所需的時間? | Please wait for a moment while we are discussing the open source issue with Sony.
6 | 播放error・ 無法顯示metadata的contexts對應 | Please check "Playback issues" sheet. | Sanshin | [3/4] Check with RK on Jira ID. | RK will check and feedback to Pega | Please wait for a moment while we are discussing the open source issue with Sony.
7 | 修正其他的問題 | Please check "Other issues" sheet | Sanshin | [3/4] Wait for Narita's report | RK will check and feedback to Pega | Please wait for a moment while we are discussing the open source issue with Sony.
8 | 語言學習機能(A-B repeat, Quick replay) | http://docs.esupport.sony.com/portable/NWZE353_E354_E355_guide/eng/contents/03/03/04/04.html | Sanshin |  | Can RK support this function ? | RK can't support this function.
9 | DPC(Digital Pitch Control)機能 | http://www.sony-asia.com/microsite/walkman_i-manuals/NWZ-E473/ct/contents/04/04/03/03.html | Sanshin |  | Can RK support this function ? | RK can't support this function.
10 | [Olive] Performance enhancement: Show Song list is slow after select play list | Sanshin |  |  | Ref. to postmortem #4 | Please wait for a moment while we are discussing the open source issue with Sony.
11 | [Olive] Waived feature: Bookmark function | Sanshin | 项目确立之后，RK会进行协助 |  | Can RK support this function ? Pega tried to develop this function based on NanoC MyFavorite function, but we give up due to MyFavorite bugs | Please wait for a moment while we are discussing the open source issue with Sony.

## Olive Playback issues
Key | Summary | Assignee | Reporter | Status | Owner | Pega Comment | Sanshin-0323
PD1272BG-1328 | DUT can not play "きもちＵＰＤＡＴＥ_.m4a". | Inoue Kazuyuki ( PDSW Kazuyuki.Inoue ) | Hiramoto Tatsuya ( SQA Tatsuya.Hiramoto ) | Deferred | Sanshin | (Cause Detail) Please refer to attachment Jira1328_mdat.jpg and Jira1328_mdat_2.jpg The data length in mdat should be 67073bytes (ref. Jira1328_mdat_2.jpg), but it becomes 1byte in mdat information (ref. Jira1328_mdat.jpg) Codec open this file with 1byte file length , so it causes error. 是否能正常撥放此歌曲? | Please wait for a moment while we are discussing the open source issue with Sony.
PD1272BG-1321 | There are the contents that meta data cannot display. | Inoue Kazuyuki ( PDSW Kazuyuki.Inoue ) | Hiramoto Tatsuya ( SQA Tatsuya.Hiramoto ) | Deferred | Sanshin | 因為混合ID3v2.2 & ID3v2.3 tags, 故無法顯示metadata, 是否能解決此問題 ? | Please wait for a moment while we are discussing the open source issue with Sony.
PD1272BG-1273 | During the music file 32kbps_48000Hz.m4a playing, it will show the file is damaged | Inoue Kazuyuki ( PDSW Kazuyuki.Inoue ) | Kao George ( PEGATRON George_Kao ) | Deferred | Sanshin | 1:53到2:03故意清為0 , 因為得不到frame header所以報demaged file error , 客人還是希望拉長zero frame的長度 , 盡量不要報錯 , 是否能滿足客人要求 ? | Please wait for a moment while we are discussing the open source issue with Sony.
PD1272BG-1263 | Olive cannot recognize the genre type of WAV music file. | Inoue Kazuyuki ( PDSW Kazuyuki.Inoue ) | Wu Joicy ( V&S Joicy_Wu ) | Closed | Sanshin | WAV檔無法解析metadata , 是否能修正此問題 ? | Please wait for a moment while we are discussing the open source issue with Sony.

## Olive Other issues
Key | Summary | Assignee | Reporter | Status | Owner | Pega Comment | Sanshin-0323
PD1272BG-1325 | Music > Folder and otherwise, sort position of some sign is different | Inoue Kazuyuki ( PDSW Kazuyuki.Inoue ) | Ishitobi Masahiro ( SDNA xMasahiro.Ishitobi ) | Deferred | Sanshin | Narita希望Folder也用All songs/Album/Artist/Genre同樣排序方式 | Please wait for a moment while we are discussing the open source issue with Sony.
PD1272BG-1324 | Original behavior of the key does not occur, when key was pushed and released during screen off and playing, at screen other than music playback screen | Inoue Kazuyuki ( PDSW Kazuyuki.Inoue ) | Ishitobi Masahiro ( SDNA xMasahiro.Ishitobi ) | Deferred | Pega | Narita QA認為與spec_of_key_operation_each_status_20151030.xlsx不符合 , 但我們只有在music playback screen實作
PD1272BG-1315 | Beep sound become sharp when playing 64kbps_8000Hz.wav | Inoue Kazuyuki ( PDSW Kazuyuki.Inoue ) | Kao George ( PEGATRON George_Kao ) | Deferred | RK | 1.RK解釋為high sample rate歌曲會干擾之後的low sample rate歌曲 (直接撥low sample rate歌曲不會) , 導致beep sound變尖銳 , 因此要做beep_stop()與之後的deinit動作 2.此問題僅在8KHz歌曲發生(11.025KHz不會) , SDK也會發生 3.已出報告但客戶認為無法解釋 , 故不上patch
PD1272BG-1310 | DUT Beep sound sometimes become sharp. | Inoue Kazuyuki ( PDSW Kazuyuki.Inoue ) | Wu Joicy ( V&S Joicy_Wu ) | Deferred | Pega | 原因為播完music, beep sample rate變數沒有被reset, 導致進入FM後錯用其他非44.1K sample rate 複製步驟為1.Play 8KHz song 2.Home->FM 3.Press key in FM (要先撥8KHz song才會), 進FM重設sample rate可解, 但客戶不上
PD1272BG-1297 | Play damaged music file error message shows"Cannot play,file format is not support" | Inoue Kazuyuki ( PDSW Kazuyuki.Inoue ) | Wu Joicy ( V&S Joicy_Wu ) | Deferred | Sanshin | 播放開始時的error訊息只有"file format is not supported", 希望能區分"file is damaged" | This is related to UI issues.
PD1272BG-1295 | HOLD Press Right/Left key on attached music, FF/FR speed is slow, the play icon changed delay 2s. | Inoue Kazuyuki ( PDSW Kazuyuki.Inoue ) | Wu Joicy ( V&S Joicy_Wu ) | Deferred | RK | 8KHz歌曲開始與結束快轉很慢, 且Play icon 要兩秒才能正確顯示, 1233的patch也可解 , 但客人不上
PD1272BG-4 | [ICX-1258 Deferred] #768 Folders list cannot be displayed correctly and music cannot be played. | Inoue Kazuyuki ( PDSW Kazuyuki.Inoue ) | Inoue Kazuyuki ( PDSW Kazuyuki.Inoue ) | Deferred | Pega | Navy的FM recording問題 | Please wait for a moment while we are discussing the open source issue with Sony.